Digital Project Management (DPMG)

Term Project: Guidelines for Student Groups

# Overview and Objectives

This project is the practical backbone of the Module 5 capstone described in the DPMG syllabus. Working in groups of five, you will run a small digital product through the full project life cycle, from a one-page idea to a working demo, using a project board (Trello or Jira) as your project record and an AI coding tool as your delivery team. The point of the exercise is not to produce clever software. It is to give you a real project to manage, so that scope, requirements, testing, and stakeholder sign-off stop being slide concepts and become decisions you actually had to make.

By the end of the project you should be able to: define a scope tight enough that a delivery team, human or AI, can build it without guessing; write requirements that another person could test against; run a sequential, phase-gated delivery on a project board; and explain, individually, exactly what you built, why, and what you would change.

# Choosing Your Project

Each group works on one project, chosen from the list below or proposed independently, subject to my approval before the end of Module 1. A good project for this exercise is small enough to build in a few weeks, has a single clear user, and needs no data or integrations you cannot get hold of. Steer away from anything that depends on real payments, real user data, or a licensed API behind a paywall.

1. Expense splitter for group trips or flatmates

2. Personal budget tracker with spending categories

3. Habit tracker with streaks and reminders

4. Simple CRM for a small business's customer contacts

5. Event RSVP and guest management tool

6. Inventory tracker for a small retailer

7. Internal helpdesk ticket tracker

8. Job application tracker for placement season

9. Recipe and meal planner with a shopping list generator

10. Library or equipment lending tracker for a department

11. Simple booking system for shared resources, such as meeting rooms or equipment

12. Feedback and survey tool with basic reporting

13. Attendance tracker for student clubs or societies

14. Basic e-commerce catalogue with a cart, no real payment processing

15. Study group scheduler that matches members' free time slots

If you would rather propose your own idea, bring a one-paragraph pitch to me before the end of Module 1. The same size and complexity limits apply.

# Team Structure

Groups of five, one project per group. How you split responsibilities is your call, but every member must own at least one phase's deliverable on the board, since that ownership is what the individual viva will test. Agree and record who leads each phase before Module 2 begins, as a short team charter at the top of your requirements document.

# Delivery Approach: Waterfall, Tracked on a Board

This project runs as a waterfall, not Agile. You will meet Agile properly in a dedicated course next term, so this course deliberately builds the sequential, phase-gated discipline that waterfall demands, the classic project life cycle covered in Module 1. Track it on a single board, either Trello or Jira, both free for a team this size. Set up six lists or columns: Requirements, Design, Build, Test, Demo, Closure. A card or ticket moves to the next stage only once its exit criteria are met, and once a stage is closed it does not reopen, with one exception: defects found in Test may go back to Build for a fix.

Trello: the free plan covers everything you need. Create one board, add six lists, and use a label per team member so ownership is visible at a glance.

Jira: the free tier covers up to ten users. Create a Kanban project, not Scrum, rename the default columns to match your six stages, and add a component or label per member.

Whichever tool you pick, the whole group uses the same board. Screenshot it at three points in the term, after Requirements, after Build, and at Closure, as your status evidence.

| Phase | Board stage (Trello list / Jira column) | Exit criteria |
| --- | --- | --- |
| Requirements | Requirements | Requirements document complete, each requirement carries a unique ID, team charter agreed |
| Design | Design | Design note complete: screens, key features, data model, tool choice for the build confirmed |
| Build | Build | Product built using an AI coding tool, all planned features implemented and tracked as cards or tickets |
| Test | Test | All test cases run, defects logged and closed, traceability matrix complete |
| Demo | Demo | Live demo delivered to the class |
| Closure | Closure | Retrospective note filed: what went to plan, what did not, and why |

# Timeline

The project starts on 17 August, when your group sets up its board and agrees the team charter. It runs to 20 September. Requirements and design are kept short so that build and test, which take longer, have the most time. Each date below is the deadline for that deliverable, not a rigid start point, use the time in between as your group sees fit.

| Date | Phase | Key deliverable due |
| --- | --- | --- |
| 20 August | Requirements | Requirements document complete |
| 27 August | Design | Design note, build tool choice confirmed |
| 10 September | Build | Working product tracked on board, prompt/iteration log begins |
| 17 September | Test | Test cases, traceability matrix, defect log |
| 20 September | Demo & Closure | Live demo, retrospective note |
| Week of 21 September (to be confirmed) | Individual viva | One-on-one viva per student |

# Building the Product: Vibe Coding with AI Tools

You are the product owner and delivery manager on this project, not the developer. Your AI coding tool is the delivery resource. That does not lower the bar on project management, it raises it, because the tool will build exactly what you ask for, no more and no less, so any gap in your requirements shows up directly in the product.

Claude is the natural first choice, since you already have access to it through the programme. If you want to compare approaches, the free tiers of Cursor, Replit, Lovable, or v0.dev all work for a project this size too. Pick one tool per group and stick with it, switching tools mid-build wastes time you do not have.

A few rules that apply throughout the build:

Keep the product to one clear purpose. If a feature is not in your requirements document, it does not get built.

Log every prompt you send and every significant response in the prompt/iteration log, in the order they happened.

Nothing is done until your group has tested it against your own test cases and logged the result.

Bugs go back onto the board as defects, not straight into a new prompt. Track them the way you would track any delivery team's defects.

At least one member per group must be able to open the product and demonstrate every feature without help, because that member may be asked to do exactly that in the viva.

# Deliverables Checklist

1. Requirements document: numbered functional requirements, with a short team charter at the top naming who owns each phase and NFR

2. Design note: screens, key features, data model, kept light

3. Working product and prompt/iteration log: the built product, plus every prompt sent and its outcome, in sequence

4. Test cases and traceability matrix: see format below

5. Project board: Trello or Jira, maintained throughout with screenshots taken at three checkpoints, after Requirements, after Build, and at Closure

6. Live demo and retrospective: a live walkthrough plus a short note on what went to plan, what did not, and what you would do differently

Traceability matrix format, one row per requirement:

| Req ID | Requirement | Test Case ID | Test Description | Expected Result | Actual Result | Pass/Fail | Board Card / Ticket |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | ... | TC1 | ... | ... | ... | ... | ... |

# Final Demo

Each group demonstrates the working product to the class, covering the problem it solves, a live walkthrough of its main features, and one thing that did not go to plan and how it was handled. Close with a two-minute retrospective: what went to plan, what did not, and what you would do differently. All five members must be present, and the floor is open to questions from me and from classmates.

# Individual Viva

The viva happens after teaching ends, once every group has completed its project. Each student sits a five to seven minute individual session with two parts. First, a common set of questions everyone answers, on the requirements, the delivery approach, and what you would change. Second, one personalised question drawn directly from your own activity on the board, Trello or Jira, for instance a requirement you wrote, a card you moved, or a defect you logged. Come prepared to explain your own contribution, not just the group's.

# Assessment (20% of the Course)

| Component | Weight | What is assessed |
| --- | --- | --- |
| Group deliverables | 10% | Completeness and quality of the six deliverables above, the working product at demo, and evidence the group worked across the term rather than in one sitting, visible from the board history |
| Individual viva | 10% | Understanding of the whole project, not just your own part, plus your ability to explain your own logged contribution on the board |

The 20% project weighting splits into two equal parts. The first 10% is a single group mark: every member of a group receives the same score for the quality and completeness of the deliverables. The second 10% is an individual viva mark: each of you is scored separately, so two students in the same group can, and often do, end up with different marks.

# A Note on Using AI Tools

Using an AI tool such as Claude to build the product is expected and required for this project, unlike coursework where AI use might otherwise need declaring. What matters is that you can account for every decision that went into what the tool built, in the prompt log and in your viva. A group that cannot explain its own product will be treated, for grading purposes, as though the product does not exist.